## Slide 1
Program today
Exam-assignment – report!
Exam-subjects – oral exam.
Theory: Comparison of methods
PAB 2018

## Slide 2
Agenda
Goal
Be able to compare and discus different systems development processes
Be able to classify Scrum and XP

## Slide 3
Systems development
To succeed we need a systematic approach concerning
The structure of the product
The process producing the product
Visions and requirements
Systems
Development
process

## Slide 4: How to choose an approach?
Define the Task at hand
Choose a process model which suits the task
Choose a method within the process model
Use the recommended techniques and tools
BUT …never be mechanistic:
Adapt the method
Perhaps combine methods
Be pragmatic
  Focus on approaches that works
Remember:
“There is no silver bullet”
Death over standard methods!
Process models
System development methods
Tools
Situation
Techniques

## Slide 5
Systems development and uncertainty
Systems development is a creative process!
Routine – Problem solving – Problem definition
In systems development many decisions are taken!
Start
Goal

## Slide 6
Types of situations
Attributes in Relation to Situation | Assignment or problem | Working practice | Uncertainty
Routine | Known | Known | Small
Problem solving | Known | Unknown | Intermediate
Problem setting | Unknown | Unknown | Large

## Slide 7: Systems development and uncertainty
Problem definition situations are characterized by symptoms, it is important to identify the problem / task behind
Problem solution situations are open, often requires an experimenting and searching approach
Routine Situations are 'easy' to handle, but may require extensive and qualified effort
 | The task is known | The solution is known
Problem definition | no | no
Problem solving | yes | no
Routine | yes | yes
Low
uncertainty
High
uncertainty

## Slide 8: How to choose an approach?
Define the Task at hand
Choose a process model which suits the task
Choose a method within the process model
Use the recommended techniques and tools
BUT …never be mechanistic:
Adapt the method
Perhaps combine methods
Be pragmatic
  Focus on approaches that works
Remember:
‘There is no silver bullet’
Death over standard methods!
Process models
System development methods
Tools
Situation
Techniques

## Slide 9: Process models (paradigms)

## Slide 10: Methods and systems development theory
  Methods have a more or less defined scope
  Methods have an underlying perspective
Methods provides guidelines for how the process should proceed:
  The sequence in which to carry out the functions
  The artefacts to produce
Experience is essential for system developers
Methods are experience put in patterns
Methods are not practical if the situation does not fit
General knowledge – systems development theory
Method Independent understanding of systems development

## Slide 11
Ideal and reality
Many methods build on a rational ideal:
  Common and clearly defined goals
  Adequate and accessible resources
  Developers can analyse their way to relevant designs and predict their consequences
System developments projects in real life:
  Starts without clearly defined goals
  Design decisions are taken without analysis of alternatives
  Great complexity
  Changing requirements
  …

## Slide 12
What’s a process model and a method?
Process models are differentiated by their sequence of activities
  For instance, first full analysis, then design …
Methods are differentiated by the content of the activities
  For instance:
    Which activities are carried out during design?
    Which models are made during analysis?

## Slide 13: Waterfall, predictive, plan driven - “The devil” is known by many names 
Requirements
Design
Implementation
Verification
Deployment
Known goals/tasks
Maintenance
Large systems
Division of work

## Slide 14
Waterfall, predictive, plan driven
The process model presupposes requirements can be specified ”up front”
Cost and time can thus be estimated based on the requirements
Fixed price contract
But what about quality?
Better than ”code ‘n’ fix”
Immediately logical and predictable
Most software is developed like this
Fixed price contract is a must
Plan
Driven
Requirements
Cost
Time

## Slide 15
Problems with the waterfall model
31 % of projects were cancelled before completion
53 % of the projects will cost more than 189% of their estimates
Only 16 % of projects are completed on time and budget
Completed projects delivered only 42% of the original requirements
Ineffective treatment of requirements is the primary cause of cancelled projects:
  13% of projects lack user input
  12% of projects have incomplete requirement specifications
  12% of projects have changing requirement specifications

## Slide 16
Iterative and incremental processes
Advanced development tools and technologies
Increased ‘time-to-market’ pressure
Need for new innovative exploration based methods
Generic model for iterative and incremental methods
Spiral model: Experimental exploration
Methods
RAD (Rapid Application Development): Development of prototypes with advances tools
UP: Iterative and incremental development of big and complex systems

## Slide 17: Spiral model - iterative og incremental
Boehm 1988
The first published
iterative og incremental method
Accept of change of requirements
Focus on continuous feedback
Gradually expansion of the system through prototypes

## Slide 18
Unified Process

## Slide 19: Waterfall vs. Iterative Process
There can be feedback loops between these steps, but the dominant practice is that a particular discipline is mostly completed before moving on to the next discipline.
In an iterative process you accomplish a small amount of each of the disciplines (requirements, analysis, design, implementation, and testing) in every iteration
Kilde: http://www.ibm.com/developerworks

## Slide 20: Agile (adaptive) processes

## Slide 21
XP - agile

## Slide 22
Scrum - Agile

## Slide 23
Value driven instead of plan driven
Goodbye to the iron triangle
Determined
Plan
Driven
Requirements
Cost
Time
Time
Resources
Requirements
Value
Driven
Estimated
Waterfall
Agile

## Slide 24: Sub functions of systems development
Analysis
Design
Realisation
Evaluation
Planning
Regulation
Decision-making
Communication
Socialisation
Performance
Management
General

## Slide 25: Main components of systems development -A methodology independent description
Design
Analysis
Realisation
Reflec-
tion
Action
Product-oriented
Process-oriented
Visions
Present
reality
Visions
Present
reality
Planning
Evaluation
Regulation

## Slide 26
Systems development - General
Decision-making
  Can take time
  Can delay the progress
Communication
  Man – man
  Group – group
  Man – machine
  Content, form, location
Socialising
  Intern informal contracts
  Project establishment – more formal contracts